## Sheet1
Project Activities and Timeline
Week No.
Planned Task | Task Owner | 15th April | 22nd April | 2nd May | 9th May | 16th May | 23rd May | 30th May | 6th June | 13th June | 20th June | 27th June | 4th July | 11th July | 18th July | 25th July | Actual | Remarks
PO Release & Test Data | TMML
[17 empty] | PO Release & Test Data | Task Complete
SRS Document | BRiOT/TMML
[17 empty] | SRS Document | Task Complete -(Got SRS document confirmation from client as on 15th May 2019)
Software Development | BRiOT
[17 empty] | Software Development | In Progress
Internal Testing | BRiOT
Internal Testing
Deployment | BRiOT
Deployment
UAT (User Acceptance Testing) | BRiOT/TMML
UAT (User Acceptance Testing)
Final Change Development & eployment | BRiOT
Final Change Development & eployment
Project Go-Live | BRiOT
Project Go-Live
Project Sign Off | TMML
Project Sign Off
BRiOT's Task
Client's Task
Joint Task (BRiOT & Client)