## Sheet1
Module | Changes | Change Type | Impact | Comment
Maintenance | In Machine Maintenance Screen, there should be field to captue the id of Maintenance person who has completed the maintenance for designated machine. | Small | Minor | Was not part of earlier scope
Maintenance | In Machine Maintenance Screen, add field to capture the cost of part replaced, when maintenance is completed. | Small | Minor | Was not part of earlier scope
Maintenance | Change from `waiting for maintenance` to `Schedule Maintenance` | Small | None
Machine Master | Provide interface to allow user to re-activate the Machine | Small | Minor | Was not part of earlier scope
Job Card | In job card print screen, provide filter for machine selection based on which user can select the machine from list, where the first process will start, accordingly, user can print the jobcard of given part number. | Medium | Minor
Job Card | Instead of Machine Group, Machine Type should be printed | Small | None | Was not part of earlier scope
Part Number | Show the Part Details based on Jobcard (Desktop and Device) | Small | None | Was not part of earlier scope
Part Number | provide interface to upload and view part Number details in pdf format | Small | Minor | Was not part of earlier scope
Production Schedule | Provide select option for different type of schedule while creating it (by default, it will be Planned Schedule). Other options are Nesting RM Optimization, Design Change | Small | Minor | Was not part of earlier scope
Production Schedule | Provide remark column In Production Schedule screen when it is not planned schedule | Small | Minor
Production Schedule | Capture the Monthly Schedule (Provide interface to upload monthly schedule once on start of the month) | Medium | Medium | Was not part of earlier scope
Production Schedule | Add column in Daily schedule - Part added due to nesting | Small | Medium
Production Schedule | Provide checkbox and text (Plan is after considering the current inventory and WIP at machine shop and open job card) while uploading daily plan | Small | None | Was not part of earlier scope
Production Schedule | Show indication on daily plan upload when the quantity goes beyond monthly plan | Big | Big | Was not part of earlier scope
Production Schedule | Allow daily plan to edit for those which are not started yet.
Production Schedule | Provide exception report while uploading the daily plan with respect to monthly for quantity goes beyond | Medium | Medium | Was not part of earlier scope
Job Card Report | Show report for open jobcard (WIP and not started) | Medium | Medium
Report based on Monthly Plan | Show Monthly Plan with respect to all daily part number quantity planned so far | Big | Big | Was not part of earlier scope
Production Schedule | Allow re-routing of part beyond defined machine group | Required to come up with solution | Critical | Was not part of earlier scope
Production Schedule | at the time of upload, provide intimation of part number when scheduled production goes beyond capacity of machine | Need to brainstorm on this as there can be multiple machines on which part number will go | Minor | Was not part of earlier scope