## Estimate
Section | Modules | Sub-tasks | Estimation (In hours) | Estimation (In days) | Estimation (In days in actual) | Actual Date | Owner
Application | Architecture | Define application architecture | 8 | 1 | 1 | Done | Dinesh Sir, Manish Sir
Front-end | Dashboard | Top Navigation Bar | 4 | 0.5
Front-end | Dashboard | Bottom Bar | 4 | 0.5
Front-end | Dashboard | Left Navigation Bar | 6 | 0.75
Front-end | Dashboard | Content Area Container | 4 | 0.5
Front-end | Login | Create UI for login screen | 2 | 0.25
Front-end | User Screen | Create user listing screen | 4 | 0.5
Front-end | User Screen | Create add user screen | 2 | 0.25
Front-end | User Screen | Create edit user screen | 1 | 0.125
Front-end | User Screen | Create deactivate user screen | 1 | 0.125
Front-end | Machine type Screen | Create machine type screen | 2 | 0.25
Front-end | Machine type Screen | Create add machine type screen | 1 | 0.125
Front-end | Machine type Screen | Create edit machine type | 1 | 0.125
Front-end | Machine type Screen | Create deactivate mchine type screen | 1 | 0.125
Front-end | Machine group Screen | Create machine group screen | 2 | 0.25
Front-end | Machine group Screen | Create add machine group screen | 1 | 0.125
Front-end | Machine group Screen | Create edit machine group screen | 1 | 0.125
Front-end | Machine group Screen | Create deactivate machine group screen | 1 | 0.125
Front-end | Machine listing Screen | Create machine listing screen | 4 | 0.5
Front-end | Machine listing Screen | Create add machine screen | 3 | 0.375
Front-end | Machine listing Screen | Create edit machine screen | 3 | 0.375
Front-end | Machine listing Screen | Create bulk upload screen | 2 | 0.25
Front-end | Machine listing Screen | Create deactivate machine screen | 1 | 0.125
Front-end | Cell listing Screen | Create cell listing screen | 2 | 0.25
Front-end | Cell listing Screen | Create add cell screen | 1 | 0.125
Front-end | Cell listing Screen | Create edit cell screen | 1 | 0.125
Front-end | Cell listing Screen | Create bulk upload screen | 2 | 0.25
Front-end | Cell listing Screen | Create deactivate cell screen | 1 | 0.125
Front-end | Costcenter Screen | Create costcenter listing screen | 2 | 0.25
Front-end | Costcenter Screen | Create add costcenter screen | 1 | 0.125
Front-end | Costcenter Screen | Create edit costcenter screen | 1 | 0.125
Front-end | Costcenter Screen | Create bulk upload screen | 2 | 0.25
Front-end | Costcenter Screen | Create deactivate costcenter screen | 1 | 0.125
Front-end | Raw material Screen | Create raw material listing screen | 4 | 0.5
Front-end | Raw material Screen | Create add raw material screen | 2 | 0.25
Front-end | Raw material Screen | Create edit raw material screen | 2 | 0.25
Front-end | Raw material Screen | Create bulk upload screen | 2 | 0.25
Front-end | Raw material Screen | Create deactivate raw material screen | 1 | 0.125
Front-end | Material type Screen | Create material type listing screen | 2 | 0.25
Front-end | Material type Screen | Create add material type screen | 1 | 0.125
Front-end | Material type Screen | Create edit material type screen | 1 | 0.125
Front-end | Material type Screen | Create bulk upload screen | 1 | 0.125
Front-end | Material type Screen | Create deactivate material type screen | 1 | 0.125
Front-end | Part Number Screen | Create part numbers listing screen | 6 | 0.75
Front-end | Part Number Screen | Create add part number screen | 4 | 0.5
Front-end | Part Number Screen | Create edit part number screen | 4 | 0.5
Front-end | Part Number Screen | Create bulk upload screen | 2 | 0.25
Front-end | Part Number Screen | Create deactivate part number screen | 2 | 0.25
Front-end | Trolley listing Screen | Create trolley listing screen | 4 | 0.5
Front-end | Trolley listing Screen | Create add trolley screen | 2 | 0.25
Front-end | Trolley listing Screen | Create edit trolley screen | 2 | 0.25
Front-end | Trolley listing Screen | Create bulk upload screen | 2 | 0.25
Front-end | Trolley listing Screen | Create deactivate trolley screen | 1 | 0.125
Front-end | Trolley type Screen | Create trolley type listing screen | 2 | 0.25
Front-end | Trolley type Screen | Create add trolley type screen | 1 | 0.125
Front-end | Trolley type Screen | Create edit trolley type screen | 1 | 0.125
Front-end | Trolley type Screen | Create bulk upload screen | 1 | 0.125
Front-end | Trolley type Screen | Create deactivate trolley type screen | 1 | 0.125
Front-end | Production schedule Screen | Create production schedule listing screen | 6 | 0.75
Front-end | Production schedule Screen | Create add production schedule screen | 4 | 0.5
Front-end | Production schedule Screen | Create edit production schedule screen | 4 | 0.5
Front-end | Production schedule Screen | Create deactivate production schedule screen | 1 | 0.125
Front-end | Job card Screen | Create job card listing screen | 4 | 0.5
Front-end | Job card Screen | Create add job card screen | 6 | 0.75
Front-end | Job card Screen | Create edit job card screen | 4 | 0.5
Front-end | Job card Screen | Create deactivate job card screen | 1 | 0.125
Front-end | Reprint Screen | Create job card reprint screen | 4 | 0.5
Front-end | Reprint Screen | Create machine reprint screen | 4 | 0.5
Front-end | Reprint Screen | Create part number reprint screen | 4 | 0.5
Front-end | Reprint Screen | Create location reprint screen | 4 | 0.5
Front-end | Reprint Screen | Create trolley reprint screen | 4 | 0.5
Front-end | Process Data feed Screen | Create process data listing screen | 4 | 0.5
Front-end | Process Data feed Screen | Create start process data feed screen | 2 | 0.25
Front-end | Process Data feed Screen | Create stop process data feed screen | 2 | 0.25
Front-end | Location Screen | Create location listing screen | 2 | 0.25
Front-end | Location Screen | Create add location screen | 1 | 0.125
Front-end | Location Screen | Create edit location screen | 1 | 0.125
Front-end | Location Screen | Create deactivate location screen | 1 | 0.125
Front-end | Location Screen | Create bulk upload screen | 2 | 0.25
Front-end | Logistics dashboard Screen | Create logistics dashboard screen | 4 | 0.5
Front-end | Logistics dashboard Screen | Create pick and drop screen | 4 | 0.5
Front-end | Re-routing Screen | Create Job card listing screen | 2 | 0.25
Front-end | Re-routing Screen | Create re-routing job card screen | 4 | 0.5
Front-end | Maintenance dashboard Screen | Create maintenance dashboard screen | 4 | 0.5
Front-end | Maintenance dashboard Screen | Create machine status change screen | 1 | 0.125
HHT UI | Login Screen | Create UI for login screen | 1 | 0.125
HHT UI | Dashboard Screen | Create UI for dashboard on HHT device | 1 | 0.125
HHT UI | Job card details Screen | Create UI for Job card details | 1 | 0.125
HHT UI | Start job card process Screen | Create UI for start job card process | 1 | 0.125
HHT UI | Stop job card process Screen | Create UI for stop job card process | 1 | 0.125
HHT UI | Stop job card process Screen | Create UI for stop job card process with reasons | 1 | 0.125
HHT UI | Logistics Screen | Create UI for Logistics/Pending items dashboard | 1 | 0.125
HHT UI | Logistics Screen | Create UI for change location screen | 1 | 0.125
Back-End | Login | Create login api | 1 | 0.125
Back-End | Machine type | Create machine type api | 1 | 0.125
Back-End | Machine type | Update machine type api | 1 | 0.125
Back-End | Machine type | Read machine type list api | 1 | 0.125
Back-End | Machine type | Read machine type by id api | 1 | 0.125
Back-End | Machine type | Deactivate machine type api | 1 | 0.125
Back-End | Machine group | Create machine group api | 1 | 0.125
Back-End | Machine group | Update machine group api | 1 | 0.125
Back-End | Machine group | Read machine group list api | 1 | 0.125
Back-End | Machine group | Read machine group by id api | 1 | 0.125
Back-End | Machine group | Deactivate machine group api | 1 | 0.125
Back-End | Machine listing | Create machine api | 1 | 0.125
Back-End | Machine listing | Update machine api | 1 | 0.125
Back-End | Machine listing | Read machine list api | 1 | 0.125
Back-End | Machine listing | Read machine list by id api | 1 | 0.125
Back-End | Machine listing | Deactivate machine api | 1 | 0.125
Back-End | Cell | Create cell api | 1 | 0.125
Back-End | Cell | Update cell api | 1 | 0.125
Back-End | Cell | Read cell list api | 1 | 0.125
Back-End | Cell | Read cell by id api | 1 | 0.125
Back-End | Cell | Deactivate cell api | 1 | 0.125
Back-End | Costcenter | Create costcenter api | 1 | 0.125
Back-End | Costcenter | Update costcenter api | 1 | 0.125
Back-End | Costcenter | Read costcenter list api | 1 | 0.125
Back-End | Costcenter | Read costcenter by id api | 1 | 0.125
Back-End | Costcenter | Deactivate costcenter api | 1 | 0.125
Back-End | Raw material | Create raw material api | 1 | 0.125
Back-End | Raw material | Update raw material api | 1 | 0.125
Back-End | Raw material | Read raw material list api | 1 | 0.125
Back-End | Raw material | Read raw material by id api | 1 | 0.125
Back-End | Raw material | Deactivate raw material api | 1 | 0.125
Back-End | Material type | Create material type api | 1 | 0.125
Back-End | Material type | Update material type api | 1 | 0.125
Back-End | Material type | Read material type list api | 1 | 0.125
Back-End | Material type | Read material type by id | 1 | 0.125
Back-End | Material type | Deactivate material type api | 1 | 0.125
Back-End | Part number | Create part number api | 1 | 0.125
Back-End | Part number | Update part number api | 1 | 0.125
Back-End | Part number | Read part number list api | 1 | 0.125
Back-End | Part number | Read part number by id api | 1 | 0.125
Back-End | Part number | Deactivate material type api | 1 | 0.125
Back-End | Trolley listing | Create trolley api | 1 | 0.125
Back-End | Trolley listing | Update trolley api | 1 | 0.125
Back-End | Trolley listing | Read trolley list api | 1 | 0.125
Back-End | Trolley listing | Read trolley by id api | 1 | 0.125
Back-End | Trolley listing | Deactivate trolley api | 1 | 0.125
Back-End | Trolley type | Create trolley type api | 1 | 0.125
Back-End | Trolley type | Update trolley type api | 1 | 0.125
Back-End | Trolley type | Read trolley type list api | 1 | 0.125
Back-End | Trolley type | Read trolley type list by id api | 1 | 0.125
Back-End | Trolley type | Deactivate trolley type api | 1 | 0.125
Back-End | Production Schedule | Create production schedule api | 1 | 0.125
Back-End | Production Schedule | Update production schedule api | 1 | 0.125
Back-End | Production Schedule | Read production schedule list api | 1 | 0.125
Back-End | Production Schedule | Read production schedule get by id | 1 | 0.125
Back-End | Production Schedule | Deactivate production schedule api | 1 | 0.125
Back-End | Job card | Create job card api | 1 | 0.125
Back-End | Job card | Update job card api | 1 | 0.125
Back-End | Job card | Read job card list api | 1 | 0.125
Back-End | Job card | Read job card by id api | 1 | 0.125
Back-End | Job card | Deactivate job card api | 1 | 0.125
Back-End | Process data feed | Create process data feed api | 1 | 0.125
Back-End | Process data feed | Update process data feed api | 1 | 0.125
Back-End | Process data feed | Read process data feed list api | 1 | 0.125
Back-End | Process data feed | Read process data feed by id api | 1 | 0.125
Back-End | Process data feed | Deactivate process data feed api | 1 | 0.125
Back-End | Location | Create location api | 1 | 0.125
Back-End | Location | Update location api | 1 | 0.125
Back-End | Location | Read location list api | 1 | 0.125
Back-End | Location | Read location by id api | 1 | 0.125
Back-End | Location | Deactivate location api | 1 | 0.125
Back-End | Logistics | Create logistics api | 1 | 0.125
Back-End | Logistics | Update logistics api | 1 | 0.125
Back-End | Logistics | Read logistics list api | 1 | 0.125
Back-End | Logistics | Read logistics by id | 1 | 0.125
Back-End | Logistics | Deactivate logistics api | 1 | 0.125
Back-End | Re-routing | Create re-routing api | 1 | 0.125
Back-End | Re-routing | Update re-routing api | 1 | 0.125
Back-End | Re-routing | Read re-routing list api | 1 | 0.125
Back-End | Re-routing | Read re-routing by id | 1 | 0.125
Back-End | Re-routing | Deactivate re-routing api | 1 | 0.125
Back-End | Maintenance | Create maintenance api | 1 | 0.125
Back-End | Maintenance | Update maintenance api | 1 | 0.125
Back-End | Maintenance | Read maintenance list api | 1 | 0.125
Back-End | Maintenance | Read maintenance by id | 1 | 0.125
Back-End | Maintenance | Deactivate maintenance api | 1 | 0.125
Database | Server installation | Install Server and configure the server | 4 | 0.5
Database | Database setup | Installation of database and configuration | 2 | 0.25
Database | Create tables | Create all the master tables required | 2 | 0.25
Integratation | Login | Login UI and Api integration | 2 | 0.25
Integratation | Machine Type | Machine Type UI and Api integration | 2 | 0.25
Integratation | Machine Group | Machine Group UI and Api integration | 2 | 0.25
Integratation | Machine Listing | Machine Listing UI and Api integration | 2 | 0.25
Integratation | Cell | Cell UI and Api integration | 2 | 0.25
Integratation | CostCenter | Cost Center UI and Api integration | 2 | 0.25
Integratation | Raw material | Raw Material UI and Api integration | 2 | 0.25
Integratation | Material type | Material Type UI and Api integration | 2 | 0.25
Integratation | Part number | Part Number UI and Api integration | 4 | 0.5
Integratation | Trolley listing | Trolley listing UI and Api integration | 2 | 0.25
Integratation | Trolley type | Trolley type UI and Api integration | 2 | 0.25
Integratation | Production Schedule | Production Schedule UI and Api integration | 4 | 0.5
Integratation | Job card | Job Card UI and Api integration | 4 | 0.5
Integratation | Process data feed | Process data feed UI and Api integration | 4 | 0.5
Integratation | Location | Location UI and Api integration | 2 | 0.25
Integratation | Logistics | Logistics UI and Api integration | 4 | 0.5
Integratation | Re-routing | Re-routing UI and Api integration | 4 | 0.5
Integratation | Maintenance | Maintenance UI and Api integration | 4 | 0.5
Application | Application | Integration of App Icon | 1 | 0.125
Application | Application | Package/Installer for Windows | 4 | 0.5
Application | Application | Package/Installer for Mac | 4 | 0.5
Testing | Testing | Testing and Bug Reporting | 40 | 5
410

## Dates
Major Tasks | Estimated Start Date | Actual Start Date | Estimated Completion Date | Actual Completion Date | Estimated Man Days | Actual Man Days
API (Back-End) | 13th May 2019 |  | 22nd May 2019 |  | 8
User Interface | 13th May 2019 |  | 31st May 2019 |  | 21
HHT Interface | 13th May 2019 |  | 24th May 2019 |  | 10
API and Userface Integration | 27th May 2019 |  | 7th June 2019 |  | 10
Internal Testing and Bug Fixing | 3rd June 2019 |  | 14th June 2019 |  | 10
Deployment to Client | 14th June 2019